## Daily Tasks
Kaiser-dela Cruz Consulting, Inc
Accomplishment Report
CASUGA, Angelika A.
Date | Task | Client Name | Endorsed to | Status
2022-03-16 | Finalize and compile updates for the RCF stating, 'Additional computation for CF4 Processing Fee on the Payment Allocation for Doctors/PF. ' | CHDG |  | Done; for testing
2022-03-16 | Discuss and escalate issue on PHIC SOA vs PARS PHIC SOA discrepancy. | BIHMI | Thea Llanado | Done
2022-03-16 | Follow-up status for implementation. | MCT | Edrian Estoque | Done
2022-03-16 | Review/Discuss conditions of PhilHealth Claims Monitoring Report, Total Medicare Receivable, Total Medicare Receivable Per Membership type to change conditions/basis. | LMC | Farra Mae Palacay | Done; for adjustment
2022-03-16 | Create and send Incident letter for the reported concern/issue happened year 2019. [as requested by the client] | CHMCI | Krystelle Loyola | Done
2022-03-14 | Review/Discuss conditions of PhilHealth Claims Monitoring Report, Total Medicare Receivable, Total Medicare Receivable Per Membership type due to some data that don't coincide . | LMC | Farra Mae Palacay/Roda Mejia | Done
2022-03-14 | Create and code conditions in compliance to the computations. | CHDG | Hector Catbagan | Done
2022-03-14 | Send sample computations for the PF Payment Allocation for approval. | CHDG | Hector Catbagan | Done
2022-03-08 | Send and Compile RT-PCR Transmittal Report Format Updates for testing phase. | LMC |  | Done
2022-03-08 | Review test samples with discrepancy on CF2 Back Part vs SOA and grouping differences of SOA vs Part2&3 Report. Adjust fn_CF2Fees, Medic_GetLoadRev, Medicrep_PartIII for the newly added revenueid for: >VAT = 95,98,96,97 | LMC | Nida Abellera | Done
2022-03-08 | Discuss tables where column data size need to be updated for the MemberName concern. |  | Nida Abellera | Done
2022-03-08 | Trace concern on RT-PCR claim, can't add on transmittal report due to unprinted cf2. Review storedproc for the auto-insert default data for RT-PCR claims. Send intructions to address this case where they manually encoded and posted the cf2 data. Because in the condition, only those claims not exists on the table executes the auto-insert storeproc else, they have to print the cf2. | LMC | Diane Galvez | Done
2022-03-08 | Send documentation for PhilHealth Features on Brokenshire version. Discuss conditions on 'This patient has previous confinement w/in 90 days' |  | Rod Eda | Done
2022-03-08 | Discuss the application of repetitive cases on Phic computation. Reflected amounts on CF2 Backpart and Transmittal Report and basis of Payment Allocation and its process. | MCDGH | Edrian Estoque | Done
2022-03-07 | Adjust and finalize updates for RT-PCR Transmittal Report Format > Medic_NewTransmittal_rtpcr > Fn_GetPHICMember > fnGetExtName > Transmittal_rtpcr.rpt | LMC |  | Done
2022-03-07 | Discuss and review updates installed from last thursday for the RT-PCR claims due to duplicate entries in tbmedpatient. And discuss to flag Covid claims for easier checking. | LMC | King Pinto | Done
2022-03-07 | Get medicare scripts backup | MCT | Henry Jabunan | Done
2022-03-07 | Give instructions to fix error on saving to not null field | LMC | Nida Abellera | Done
2022-03-07 | Give instructions and followup SOA, and Part2&3 report testing outcome for out/inpatient with PNF, Non-PNF and Pharmacy Supplies charges. | LMC | Nida Abellera | Done
2022-03-07 | Give instructions and updates for the latest version of PHIC VSS > Medic_GetAdmMedicareType > get_PhicTypeCode > Medic_GetDoctorPF > tbAdmPHICTable.TypeCode > tbmedlogs.Mod_Version > tbmedmenu data | LANAO Clients | Mary Joy Sayson | Done
2022-03-04 | Send scripts to trace issue regarding rt-pcr claim. A case that meet the conditions to auto-insert required fields. Review/Execute updates for auto-insert required fields. > Medic_SavePHICSOA | LMC | Diane Galvez | Done
2022-03-04 | Give instructions and followup tagging of PNF items , SOA, and Part2&3 report testing outcome for out/inpatient with PNF, Non-PNF and Pharmacy Supplies charges. | LMC | Nida Abellera | Done
2022-03-04 | Follow-up concern regarding corrected data in old server which wasn't implemented in new server. | BIHMI | Mary Joy Sayson/ Thea Llanado | Done
2022-03-04 | Discuss report's conditions, send script, instructions to trace concern on Missing entry of claim on Unstransmitted Claims Report sorted by Last day of Submission | LMC | Farra Palacay-Sanchez | Done
2022-03-04 | Review execution of Medic_AutoComputeCharges/ Medic_AutoComputeChargesOP in Philhealth exe versions from the current version installed on client | LANAO Clients | Mary Joy Sayson | Done
2022-03-03 | Adjustment on the ff: Medic_inserttemptable > exclude NBB sa net of discount Medic_SaveActualComputation_New_Package > compute actual deduction to capture decimals Medic_AutoComputeCharges > minimize retrieving time charges | LANAO Clients | Mary Joy Sayson | Done
2022-03-03 | Discuss and review the long time pending testing of updates regarding SOA. Discuss issue regarding rth claims dues to SOA requirements that were not met. | R1MC | Nida Abellera | Done
2022-03-03 | Follow-up testing updates for SOA and Part2&3 report. | LMC | Nida Abellera | Done
2022-03-03 | Create/Design template for RT-PCR Transmittal Format > Rpt File > Stored Proc > Source Code | LMC |  | Ongoing
2022-03-01
2022-03-01 | Design/Code PF Payment Allocation's Additional entry for Processing Fee | CHDG |  | ongoing
2022-03-01 | Dicuss/Review request of additional on tagging of w/ Deduction on Payment Allocation of Professional Fees | LMC | Roda Mejia | Done
2022-03-01 | Discuss RCF on creating Legend for CF4 Verified claims for easier identification/processing. Support on CF4 Verfication process and details. | CHDG | Hector Catbagan | Done
2022-03-01 | Discuss RCF on Additional field for the computation of Processing Fee on Payment Allocation for Professional Fees. | CHDG | Hector Catbagan | Done
2022-02-15 | Noticed and Fix bug on loading Total Actual HCI Bill Noticed and Fix bug on saving Doc Specialization | PMSH | Nida Abellera | Done
2022-02-15 | Discuss/Followup client's status | MCT | Henry Habunan | Done
2022-02-15 | Design Report Template for RCF 'To include RTPCS and Covid categories in the list of untransmitted claims report' | LMC |  | ongoing
2022-02-15 | PMSH Trace/Fix issue on PHIC discrepancy for patient. Correct tagging of medicare items. Adjustments on the ff stored proc: Medic_GetTempActualAmounts Medic_SavePHICSOA_Package Medic_AutoComputeChargesOP Medic_InsertTempTable Medic_SaveActualComputation_New | PMSH | Nida Abellera | Done
2022-02-14
2022-02-14 | Discuss Claim Refiling process and the client's current setup of PHIC Recomputation | LANAO Clients | Mary Joy Sayson | Done
2022-02-14 | Design Report Template for RCF 'To include RTPCS and Covid categories in the list of untransmitted claims report' | LMC |  | ongoing
2022-02-11 | Trace/Fix discrepancy on phic comptuation. Reason: incorrect tagging of medicare items. | CHDG | Hector Catbagan | Done
2022-02-11 | Request for adjustment on report Claim Filed and Payment Monitoring, MedicRep_PhilhealthClaimFiled_PaymentMonitoringReport. Exclude posted claims with 0 phic deductions | LMC | Nida Abellera | Done
2022-02-10 | Discuss RCF: Additional computation for Processing Fee 1% before VAT | CHDG | Edrian Estoque | Done
2022-02-10 | Change setup for PHIC computation to NET of Discount. Updates: >Medic_InsertTempTable(storedproc) >SOA_Summarized_Columns_PHIC_Split.rpt | LANAO Clients | Mary joy Sayson | Done
2022-02-10 | Followup 2 RCFs | LMC | Nida Abellera | Done
2022-02-10 | Revise: Daily Medicare Claims Summary (Inpatient, Outpatient, Hemodialysis, All) Create reports: Daily PhilHealth Claims Summary(Covid, RT-PCR) MedicRep_DailyMedicareCensus_NewVer(new storeproc) vwMed_PatientMaster(revise view) DailyMedicareCensus_NewVer.rpt (new) | LMC |  | done; for testing
2022-02-09 | Discuss C19FRP process/setup | PMSH | Nida Abellera | Done
2022-02-09 | Discuss pending RCF and new RCF regarding Payment Entry | CHDG | Hector Catbagan | Done
2022-02-09 | Trace/Fix issue on encoded PF Phic deduction. A consolidated account. PF charges on patient's outpatient acct. Revise: Medic_SaveDoctorPF (storedproc) | CHDG | King Pinto, Hector Catbagan(IT) | Done
2022-02-09 | Trace/Fix issue concerning double discount computation when HMO patient case Fix: Revise stored proc Medic_SaveActualComputation_New >removed SSDC itemid for saving Discounts since Net of Discount is already the existing setup (since the Upgrade) | PMSH | Nida Abellera | Done; thru remote
2022-02-08 | Support and discuss Doctor's PHIC accredidation restrictions/exemptions. | NKTI | Mariz Luis (IT) | Done
2022-02-08 | Trace discrepancy on PHIC computation. Fixes: stored proc Medic_SavePHICSoa_package | LMC | Nida Abellera | Done
2022-02-08 | >Finalization of Report Design >Programming >Compile Updates >Send Updates to Support for Testing >Install Updates | LMC | Nida Abellera | Done
2022-02-08 | > Send out PNF Guidelines and Requirements for the PNF Updates. | MCDGH | Edrian Estoque | Done
2022-02-07 | >Discuss RCF for PhilHealth Filed Claims and Payment Monitoring Report >Construct/Design Storedproc, functions and Report Template -Medicare..MedicRep_PhilhealthClaimFiled_PaymentMonitoringReport -PhilhealthFiledClaimAndPaymentMonitoringReport.rpt | LMC | Roda Mejia (phic end-user) | ongoing
2022-02-07 | Trace discrepancy on PHIC computation. Fixes: Recompute | LMC | Nida Abellera | Done
2022-02-03 | Reply inquiry regarding databases in Test Server. Planning to overwrite the existing data and retaining pending updates. | NKTI | Mariz(IT) | Done
2022-02-03 | Trace error 'String or binary data would be truncated.' executing stored proc Medic_InsertTransmittal2015 Sent script to check/review data to be save on table. Fixes: Adjust column datasize; tbmedTransmittal.Confinement varchar(1000) | NKTI | Mariz Luis(IT) | Done
2022-02-03 | Extract 2017 - 2021 detailed data of 'Claim Filed' and 'Payment Received' from Claims Monitoring Report | LMC | Roda Mejia (phic end-user) | Done
2022-02-03 | Send SOP for tracing stored data regarding PF Payments. | BIHMI | Mary joy Sayson | Done
2022-02-03 | Trace discrepancy on the ff reports: >PhilHealth Claims Processing Performance Yearly >Census Report Details PhilHealth Admission Details Adjustment on the ff store procs: >MedicRep_YearlyProcessPerformance_new_NewFormat >MedicRep_CensusReport_PHICAdmissionYearly Causes/Fixes are the ff: >inpatient acct stored in patient_data..tboutpatient table (old bug of registration; raised thru group msg; Fixed on DLL, include isnumeric() function on Philhealth store proc reports.) >missing data or invalid data stored:'MedicareType' of selected PhilHealth claims. Extract/Compile list of Claims for correction. | LMC | Roda Mejia (phic end-user) | Done
2022-02-03 | Adjust stored proc Medic_GetProcedureDates for retrieving Hemo procedure dates based on charges saved in Inventory..tbinvstockcard | NKTI | Mariz Luis(IT) | Done
2022-01-28 | check-in/upload updates for the week | VSS |  | Done
2022-01-28 | discuss other concern from previous meeting | NKTI | Mariz Luis(IT) | Done
2022-01-28 | check current process/setup in SC that has been raised from the previous meeting | NKTI |  | Done
2022-01-28 | add replace(string, "'", "''") for free typing entries to eliminate syntax near ' | LMC |  | done
2022-01-28 | follow-up raised issue pertaining to NTP Card No. | AUFMC | Marissa Beltran(Phic end-user) | Done, fixed
2022-01-27 | Meeting with NKTI staff regarding RTH claims, LMC process demo @2PM to 5:30PM | NKTI | Philipp Kaiser, Mariz Luis, NKTI staff | Done
2022-01-27 | send instructions to fix the issue with the required field NTP Card No. | AUFMC | Marissa Beltran(Phic end-user) | Done
2022-01-27 | implementation of the updates for Doctor's PHIC Accreditation validation request. | AUFMC | Nida Abellera | Done
2022-01-27 | revise stored proc MedicRep_ReturnedToHospital_NEW basis of refiled date | LMC | Nida Abellera | Done
2022-01-27 | add replace(string, "'", "''") for free typing entries to eliminate syntax near ' |  |  | ongoing
2022-01-26 |  | VSS
2022-01-26 | discuss updating record for Discharge Date in Philhealth and if master record is affected. |  | Rod Eda | Done
2022-01-25 | apply updates in VSS / apps.gomedsys.com |  |  | Done
2022-01-25 | reply inquiry concerning with the RCF for Doctor's PHIC Accreditation validation request. | AUFMC | Gloria Pacheco (Phic end-user) | Done
2022-01-25 | Discuss regarding Inquiry for Monthly version of Daily Medicare Summary Report. >Sent instructions , Update/Insert script for activating report >Sent revised Stored Proc MedicRep_MonthlyPHICReport for the request report >Sent Create table script for Billing..tbBillSOAReference | CHMCI | Evelyn Manzano | Done
2022-01-25 | resume dicussion with the request for Filed Claims Report | Seamens-Manila | Edrian Estoque | Done
2022-01-24 | answer query where to check the logs for Initial and Final Diagnosis adjusments/activities |  | Verna Ledda | Done
2022-01-24 | Discuss concern regarding inquiry on Filed Claims Report and their current status and version. Sent instructions to check the existence of concerned report and suggest other reports they can use in case. Sent Report file and stored proc Advise to make the client decide about the basis of the report since the current basis is on CF1 data which they don't use. (to indicate in RCF) | Seamens-Manila | Edrian Estoque | Done
2022-01-24 | Discuss and follow-up correct Philhealth Classification, Product Classification, PNF, ARSP tagging of Inventory Items. | MCT | Henry Jabunan | Done
2022-01-21 | uploaded week updates on VSS |  |  | Done
2022-01-21 | adjustment on Medicare..MedicRep_IndividualXML and Medicare..MedicRep_PatientXML for duplicate zipcodes issue especially NCR Cities | AUFMC | Evelyn Manzano | Done, thru remote
2022-01-21 | fix issues regarding Philhealth Transmittal with error 'Already added'. User error, wrong tagging of transmittal details. 1592513B 1592809B 220299 1592477B 220384 1592519B 1592646B 220434 220433 220395 | AUFMC | Marissa Beltran (phic end-user), Eumart Valdez(IT) | Done, thru remote
2022-01-21 | Updates of RCF on Searching/Printing of Philhealth Logs for CF2 and CF4 >vwMedPatientLogs >Medic_LoadPatientLogs >PatientLogs.rpt | CHDG | Hector Catbagan(IT) | Done, sent thru skype
2022-01-20 | uploaded week updates on VSS |  |  | Done
2022-01-20 | Discuss and reply queries regarding CSF issue not reflecting doctors. CSF depends on client's setup | LANAO Clients | Mary joy Sayson | Done
2022-01-20 | Reply inquiries regarding error on loading of CF4 Entry due to duplilcate entries. |  |  | attempt to remote and trace but remote unit not available
2022-01-19 | discuss RCF request for CF2 and CF4 Logs Searching and Printing added logs on CF1, CF2 | CHDG | Edrian Estoque | Done
2022-01-19 | follow-up testing results for Doctor's PHIC Accreditation validation request. | AUFMC | Nida Abellera | Done
2022-01-18 | reply inquiry regarding discrepancies in 2 computation tables. Sent fix. |  | Majoy Sayson | Done
2022-01-18 | discuss process and continue the adjustments for PNF Updates. Compile updates and sent instructions for the updates. | SLUH | Evelyn Manzano | set updates for testing thru email
2022-01-17 | reply queries to trace/ simulate the possible cause about discrepancies on phic computations. | LMC | Nida Abellera | Done
2022-01-17 | discuss RCF for Disease Index Report and Searching | BIHMI | Thea Llanado(IT) | Done
2022-01-17 | discuss process and start the adjustments needed for PNF updates | SLUH | Evelyn Manzano | Done
2022-01-14 | Check-in source code updates for the week |  |  | Done
2022-01-14 | sent intructions for recomputation process, support minor issues encountered | LMC | Nida Abellera | Done
2022-01-14 | add Disease Index Report and Searching | BIHMI | Thea Llenado(IT)
2022-01-14 | trace discrepancy on computed amounts under RA. Adjustment on the ff: >Medic_SaveActualComputation_New_Package >Medic_SavePHICSOA_Package | LMC | Nida Abellera | Done
2022-01-13 | work at lmc
2022-01-12 | sickleave
2022-01-11 | work at lmc
2022-01-10 | attend concerns regarding: >PHIC Refund report >Return to Hospital report >Unpaid Report >Refiled Date Entry | LMC | Roda Mejia(Phic end-user) | done
2022-01-10 | Added validation of Doctor on Claim Form 1 Entry's Saving. CF1 Saving Restrictions: 1. If Patient's: >Admission date is not within the Doc's PHIC validity period. 2. If Doctor's: > PHIC validity period is expired. > Without PHIC Accreditation Number. > PHIC validity period will expire in [No. of Days] days. [Prompt Message Only, can still proceed] Added BuilFile and logs for Doctor's PHIC Accreditation details. Updates: **column tbmedhospital.EnablePFPHICValidCF1 tbmedForm1.employernum tbmedForm1.DoctorId **table tbmedLogs_BuildfileDoctors **stored_proc Medic_LoadDoctors Medic_GetForm1AttendingDoc **new exe file version 6.1.0.157 | AUFMC | Nida Abellera | Done; sent updates for testing
2022-01-10 | Activate Patient's Logs report and searching Updates: >Medic_LoadPatientLogs >Medic_LoadPatients >vwMedPatientLogs | CHDG | Hector Catbagan(IT) | Done
2022-01-10 | attend inquiries for Daily report on phic processing changes on patient's files e.g. CF4, CF2. | CHDG | Hector Catbagan | Done
2022-01-10 | attend inquiries for SOA discrepancy issue | LMC | Diane Galvez | Done
2022-01-10 | attend inquiries regarding RCF for Doctors Validation | AUFMC | Jeremiah Gatus | Done
2022-01-10 | attend concerns for discrepancy on SOA; Solution: recompute due to missing input | BIHMI | Thea Andrea (IT) | Done
2021-10-27 | 1.PAYMENT COLLECTION RECEIVED(UDNERPAID ACCOUNTS) > To enable All option in Membership Type > To put Heading as UnderPaid Claims > Separate Admission and Discharge date of confinement > To put PF portion in UnderPayment. | LMC |  | Done
10/262021 | Adjustment to roundoff to whole number then ff: >Avg Days Hospital >Avg Days PhilHealth Updates: MedicRep_InsertAVG_YearlyProcessPerformance_newFormat Fn_GetClaimSeriesNo MedicRep_TotalReceivable_All | LMC |  | Done
2021-10-25 | MedicRep_TotalReceivable_All
2021-10-25 | Trace issues, discuss current and future process of posting PF and Phic Deductions. | PMSH | Nida Abellera, Randy(IT) | Done
2021-10-25 | Create scripts, adjust stored procs for PNF Updates; > Insert Module Settings > Switch PNF Circular 20210012 > vwMed_PatientMaster > vwInvMasterMedicines > fn_isPxPNFCirc20210012 > fn_isMedicine_PNFCirc20210012 > Medic_GetTempActualAmounts > Medic_SavePHICSOA_Package > Medic_GetCompensable | BIHMI |  | Almost Done
2021-10-25 | Create, review Claims Monitoring; trace, extract and send copy of data. | LMC | Nida Abellera | Done
2021-10-25 | Review and reply inquiries concerning Denied tagging conditions | LMC | Nida Abellera | Done
2021-10-22 | Check-in source code updates for the week |  |  | Done
2021-10-22 | Create/send script to remove Old/Unnecessary Reports | MCT, MCDGH | Henry Jabunan, Edrian Estoque | Done
2021-10-22 | Attend and discuss inquiries regarding PhilHealth Upgrade; Adjustment on stored procs and current data(live/test) | PMSH | Randy, Nida Abellara | Done
2021-10-22 | Create/send script to remove unnecessary Reports based on list to be provided by client | PMSH | Randy, Nida Abellara | Pending (list)
2021-10-22 | Discuss Transmittal process | AUFMC | Nida Abellera | Done
2021-10-22 | Reply inquiry regarding Paid and Unpaid claims | CHDG | Hector Catbagan(IT) | Done
2021-10-22 | Discuss request for revision of Denied process. | LMC | Nida Abellera | Done
2021-10-22 | Create scripts, adjust stored procs for PNF Updates; send updates > Insert Module Settings > Switch PNF Circular 20210012 > vwMed_PatientMaster > vwInvMasterMedicines > fn_isPxPNFCirc20210012 > fn_isMedicine_PNFCirc20210012 > Medic_GetTempActualAmounts > Medic_SavePHICSOA_Package | PPMC | Nida Abellera | Done; for testing
2021-10-22 | Discuss and attempt to fix Cashier's receipt concern | ARCH | Jo-an Buncio | Done
2021-10-22 | Finalize and send update for PF grid adjustment: > frmMedComputationACR.frm, frmMedComputationOPACR.frm - Doctor's Name column (font) - column's grid to be resizable - to disable Save button if deductions already posted - to disable manual encoding of Doctor; all shld be charge from Billing. | PMSH | Nida Abellera | Done
2021-10-21 | Finalize and send update for PF grid adjustment: > frmMedComputationACR.frm, frmMedComputationOPACR.frm - Doctor's Name column (font) - column's grid to be resizable - to disable Save button if deductions already posted - to disable manual encoding of Doctor; all shld be charge from Billing. | PMSH | Nida Abellera | Done; to send
2021-10-21 | To load Doctor's PF regardless if cancelled/revoked or not To load PF regardless with or without phic deductions Update: storedproc Medic_GetDoctorPF | PMSH | Nida Abellera | Done
2021-10-21 | Issue: Patient 223506 Discrepancy on computed deductions Action done: trace acct's transactions; review stored proc conditions; manual execution of stored proc for computation returns exact amount to the stated actual deduction ; No adjustment but to resolve, needs to recompute. | AUFMC | Nida Abellera | Done
2021-10-21 | To reply inquiries regarding their new requests. To follow-up questions on their new requests. To suggest to discuss these on NKTI skype group for transparency and so others are aware. | NKTI | Mariz Luis(IT) | Done
2021-10-21 | To check Inventory items tagged as MDRP, isSenior = 0 and with discount (for tracing discrepancy on discount computations) To suggest double checking of reflected Total Actual Charges on Discount Table Billing(not tally on SOA actual charges) | MCDGH | Edrian Estoque | Done
2021-10-21 | Discuss Philhealth computation's setup | AUFMC | Nida Abellera | Done
2021-10-21 | Resend and remind PNF requirements Reply inquiry on ARSP tagging Request Medicare script copy | BIHMI | Mary Joy Sayson | Done
2021-10-21 | Discuss PhilHealth Monitoring basis: > RTH Claims > RTH Amount Claims Remarks: only those Claims tagged as RTH without payment | LMC | Nida Abellera | Done
2021-10-21 | Follow-up and discuss status of PNF tagging; request Medicare script copy | PPMC | Nida Abellera; Evelyn Manzano | Done
2021-10-20 | Inquiries: Discrepancy and basis of 2 reports Action Done: > trace discrepancy on loading: - PhilHealth Claims Monitoring - Filed Claims Amount - Census Report - Amount Claims > review conditions Updates: MedicRep_PhilhealthClaimsMonitoringReport | LMC | Nida Abellera | Done
2021-10-20 | Inquiry: basis of 2 reports: > Processing Performance Report > PhilHealth Claims Monitoring Action Done: remote and review conditions | LMC | Nida Abellera | Done
2021-10-20 | Inquiry: Fix on loading rpt file Action Done: > To send/register intwdlib.dll and crviewer.dll |  | Verna Ledda | Done
2021-10-20 | Request detailed discount computation in Billing to check if there's a problem on computation of might have other conditions aside from isSenior tagging | MCDGH | Edrian Estoque | Done; request still pending
2021-10-20 | Attend inquiries regarding Patient TAN PhilHealth Computations concerning PNF Circular. > Updates production for PNF Circular is to be scheduled. > Temp Fix: Patient is Covid case. To cover Non-Medicare Item(Internal process treated as NonPNF), to temporarily tag as Medicare. | BIHMI | Mary Joy Sayson | Done
2021-10-19 | Discuss requirements for PNF Circular Updates | MCDGH | Edrian Estoque | Done
2021-10-19 | Issue: Patient 2104810 incorrect loading of HCI package amount when reloading data. Action Done: trace thru remote; instructed Support to correct the Caserate Amount in BuildFile(PHIC) Findings: Incorrect encoded Case rate amount. | MCDGH | Edrian Estoque | Done
2021-10-19 | Issue: Patient 2104810 discrepancy on PHIC deduction. Action Done: trace thru remote, Extract patient's charges proof of computation discount based on agreed basis which is isSenior tagging. Findings: Billing Module and PHIC Discount computation doesn't much. | MCDGH | Edrian Estoque | Done
2021-10-19 | Discuss upgrade issues. | PMSH | Nida Abellera | Done
2021-10-19 | Issue: Excess Amount of SOA and CF2 didn't much. Action Done: Discuss basis of the Excess Amt. Initial Findings: If Amt After Discount is lesser or equal to CaseRate Amount, the default value is 0.00 Updates: Pending; waiting for the rpt file. | LMC | Nida Abellera | Done
2021-10-19 | Inquiry: 'Payment Received' amount basis on PhilHealth Claims Monitoring Report Action Done: Review conditions stated on RCF and storedProc MedicRep_PhilhealthClaimsMonitoringReport Findings: Payment Received amount based on discharge date. All discharges with payment under the stated month. | LMC | Nida Abellera | Done
2021-10-19 | Issue: No return data when reloading Computation details (Auto-Computation Window) Action Done: Trace and backend data thru remote; include isnull(@value, 0) Findings: Fields contains null values Updates: Views vwIcdRvs | BIHMI | Thea Llanado(IT) | Done
2021-10-19 | Issue: No return data after encoding Employer details Action Done: trace and update thru remote; To adjust add replace(@value, '-','') Findings: Query in 'Where' clause doesn't recognize Employer No. that contains dash. Updates: Storedproc Medic_GetForm1 | BIHMI | Thea Llanado(IT) | Done
2021-10-18 | - request copy of StoredProc (for inquiries of data reflecting on both Report): > MedicRep_CensusReport_PHICAdmissionYearly > MedicRep_PhilhealthClaimsMonitoringReport - request to check basis of Census Report > send script to check discrepancy on Total Claims - request to extract data of discrepancy > send script to check claims with reset Phic Computation | LMC | Farra Mae Sanchez | Done
2021-10-18 | - Attempt discussion: > To default Admission Diagnosis and Final Diagnosis once C19T1 is computed in the PhilHealth Module. > To default C19T1 in the PhilHealth Data Entry in the Special consideration. | NKTI | Mariz Luis | Done; to be continued (person On-Leave)
2021-10-18 | - Issue: Patient 202101671, CF2 and SOA discrepancy under Professional Fees' Excess Column. Work Done: trace thru remote Findings: Refund and Payments not included in CF2 under Amt after Application of Discount (PF), whereas included in SOA under Payment/Discount. In conclusion, these two entities are technically not equal. | ARCH | ARCH IT | Done
2021-10-18 | - Follow-up queries for PNF Updates request: > ZBenefit Availble? > Covid Isolation Packages Available? > ARSP Membership? | BIHMI | Majoy Sayson | Done
2021-10-18 | - discuss previous updates in connection with the issue: 'Subsript out of range' > Adjustment: Medic_GetCompensableNew | MJSH | Majoy Sayson | Done
2021-10-15 | - test sample patients to Auto-load the ff information to CF1 Entry from E-claims: > Patient's Relationship to Member > Member Info > Employer Info | NKTI | Mariz Luis(IT) | Done
2021-10-15 | - discuss computation of discount depends on the total discount from Billing (Equally distributed per item on PHIC) | MJSH | Majoy Sayson | Done
2021-10-15 | - revise SOA_Summarized_Columns_PHIC_SPLIT.rpt to suppress the ff column except Professional Fees: > 1st Case Rate Amount > 2nd Case Rate Amount > Excess | MJSH | Majoy Sayson | Done
2021-10-15 | - reply inquiries regarding formatting pages on Crystal Report |  | Nida | Done
2021-10-15 | - follow up feedback for MMHR issue reported. | BIHMI | Thea Llanado(IT) | Done; Fixed
2021-10-15 | - revise CheckRelationship Function for better loading of data. | NKTI |  | Done
2021-10-14 | - discuss list of request under submitted PRF. | NKTI | Mariz Luis(IT) | Done
2021-10-14 | - discuss concerns regarding PF Payments with and without deduction. | LMC | Roda Mejia(Phic end-user) | Done
2021-10-14 | - trace and discuss submitted issue regarding MMHR. | BIHMI | Thea Llanado(IT) | Done
2021-10-14 | - reply inquiries regarding raised concerns (not detailed) from Ma'am Marilu, but as discussed with Ma'am Nida, those were old concerns and already discussed with PMSH staff and Sir Rodney. | PMSH | Philipp Kaiser | Done
2021-10-14 | - discuss Denied current conditions and recall/trace details of condition/feature. Current condition: Reset PHIC computation and reflect as receivable. Suggested to file RCF to document any adjustment they want for the new condition. | LMC | Nida Abellera | Done
2021-10-14 | - discuss conditions of PF Payment For Uploading to Acctng - With and Without Deductions - fix adjustments on the following: > MedicRep_PaymentPFForAccUploading > prjMedicare.vbp/frmView for passing property's data type | LMC | Nida Abellera | Done
2021-10-13 | - SL due to no current and home quarantine
2021-10-12 | - EL due to no current and severe storm signal
2021-10-11 | - trace Denied Report references due to issue that was raise with the same dates reflecting on report. Remarks: user error, didn't encode the date and so default date is being saved. | LMC | Nida Abellera | Done
2021-10-11 | - attend queries and send instructions for missing report file issue reported by Ma'am Evelyn Manzano | CHMCI | Evelyn Manzano | Done
2021-10-11 | - discuss if setting beginning balance for Philhealth Receivable is applicable. Note: Beginning balance are for accounts not available in system. | BIHMI | Joan Buncio | Done
2021-10-11 | - request for sample entry from PARS for Manual Posting | ARCH | Joan Buncio | Done
2021-10-11 | - adjust fn_cf2Fees for loading duplicate entries(old data year 2003 backwards) in table tbmedactual. | LMC | Nida Abellera | Done
2021-10-08 | - check in week's updates to VSS |  |  | Done
2021-10-08 | - sent new exe file to fix bug on Searching Patient under Payment Allocation | SLUH | Evelyn Manzano | Done
2021-10-08 | - trace discrepancy in excess of SOA and CF2 due to Company Discount, PF discount | ARCH | King Pinto, ARC | Done
2021-10-08 | - discuss Receivable Report issue | LMC | Farra Sanchez | Done
2021-10-08 | - discuss requirements for PNF Updates | BIHMI | Mary Joy Sayson | Done
2021-10-08 | - send trace script and instructions for Batch Payment Allocation issue | SLUH | Evelyn Manzano | Done
2021-10-07 | - support/trace/attend concern on PNF Updates Adjustments: > Medic_AutoComputeCharges > Medic_AutoComputeChargesOP | AUFMC | Nida Abellera, Nhikz | Done
2021-10-07 | - support/discuss conditions for effectivity of NET of Discount in Phic Deduction (for testing purposes) | BIHMI | Mary Joy Sayson | Donenila ng paraan jan.
2021-10-06 | - support/trace/attend concern on PNF Updates | AUFMC | Gloria Pacheco/Nida Abellera | Done
2021-10-06 | - discuss Circular 2021-0012 stating to reflect actual total charges if Caserate amount is higher. - adjustments(for testing): > Swtich off DistributeWholePackage > Medic_SavePHICSOA_Package | BIHMI | Mary Joy Sayson | Done; sent updates for testing
2021-10-06 | - send new exe file for minor bug | BIHMI | Thea Llanado | Done
2021-10-05 | - support/trace/attend concern on PNF Updates | AUFMC | Gloria Pacheco/Jeremiah Gatus/Nida Abellera | Done
2021-10-05 | - create New Report(w/RCF) - Daily Transmittal Report > Updates: Stored proc, Rpt File, Exe File - MedicRep_DailyTransmittalReport.sql - DailyTransmittalReport.rpt | BIHMI | Thea Llanado | Done, Sent updates thru skype
2021-10-05 | - discuss the following: > Claim Form 3 adjustment for internal use > Conditions to edit C19FRP package amounts > Reference of reflected Claim amount on Transmittal Report | MJSH | Mary Joy Sayson | Done
2021-10-05 | - discuss PMSH Upgrade concern | PMSH | Nida Abellera/Philipp Kaiser | Done
2021-10-05 | - extract data for Professional Fees Payment W/ Deduction Report, Professional Fees W/out Deduction Report with cut-off September 16-29, 2021 for Accounting purposes, requested by Ma'am Roda. sent thru email. | LMC | Farra Sanchez/Roda Mejia/Ruschelle Valmores | Done
2021-10-04 | - trace/revise View: VwMedicines for fix on loading returned items if Department's stocks or e-cart | LANAO Hospitals | Mary Joy Sayson | Done
2021-10-04 | - discuss PMSH Upgrade | PMSH | Nida Abellera | Done
2021-10-04 | - support/trace/attend concern on PNF Updates | AUFMC | Nhikz/Gloria Pacheco/Jeremiah Gatus/Nida Abellera | Done
2021-10-02 | - support/trace/attend concern on PNF Updates Additional adjustments: > Medic_GetTempActualAmounts - Fix for discount issue | AUFMC | Gloria Pacheco/Jeremiah Gatus/Nida Abellera | Done
2021-10-01 | - discuss request on ER registration date as Admission Date for admitted patient from ER (PhilHealth purpose only) | NKTI | Mariz Luis | Done
2021-10-01 | - support/trace/attend concerns on PNF Updates Additional adjustments: 1. Stored Proc - > MedicRep_DetailedMedicareItems 'B. DRUGS AND MEDICINES - PNF' 'B. DRUGS AND MEDICINES - NonPNF' 'B. DRUGS AND MEDICINES - ARSP' > Medic_ChargesPatient PHARMACY MEDS/DRUGS (ARSP) PHARMACY MEDS/DRUGS (PNF) PHARMACY MEDS/DRUGS (Non-PNF) PHARMACY SUPPLIES PHARMACY RETURNED MEDS/DRUGS (ARSP) PHARMACY RETURNED MEDS/DRUGS (PNF) PHARMACY RETURNED MEDS/DRUGS (Non-PNF) PHARMACY RETURNED SUPPLIES > Medic_SavePHICSOA_Package - Fix for discount issue > Medic_GetTempActualAmounts - Fix for discount issue 2. Report > MedicareItemsDetailed.rpt > Charges.rpt | AUFMC | Nhikz/Gloria Pacheco/Jeremiah Gatus/Nida Abellera | Done
2021-09-30 | - attend meeting with NKTI staff, Sir Philip and Ma'am Nida Billing >SOA - Get ER Date >include Summary to main SOA (sample to follow) >PHIC Deduction - reflect total charges if less than Case rate amount (for User confirmation ) PhiHealth > Reflect ER Registration date as Admission Date (Auto) > Default 1 to number of days if OPD > PHIC Deduction - reflect total charges if less than Case rate amount Nurse > Checking height and weight before sending discharge Chemo, Endo, IVASC > require dosage when charging medication OPD > To allow currently admitted patient to be registered as OPD, if Covid19 Patient with other Medical Case (mainly for Philhealth purposes) | NKTI |  | Done
2021-09-30 | - send intructions for missing data in CF2 report. - remote and trace CF2 issue Solution: >Uncheck Can Grow for Admission Dx Field >To suggest user to change their way of encoding Admission diagnosis to fit in the alloted field. | MDH | Nida Abellera | Done
2021-09-30 | - send instructions for tracing issue regarding Receivable report | LMC | Nida Abellera | Done
2021-09-30 | - reply inquiries and process regarding Refiling Re-filed Denied Claims - trace concerned patient's refiling details | BIHMI | Thea Llanado | Done
2021-09-30 | - Issue: decimal Discrepancy on PHIC deduction Solutions: Additional adjustment on itemized discount computation for Senior and PWD Formula for to get exact discount = (Actual/ Total Actual) * Total Discount from Billing > Medic_GetCompensableNew > Medic_GetLoadCompensable > New Exe File > Medic_DumpCompensable.Amount datatype from Money to Float > Medic_Compensable.Amount datatype from Money to Float | MJSH | Mary Joy Sayson | Done, for testing
2021-09-27 | - trace Philhealth deductions deficiency due to the discrepancy of PHIC's itemized senior discount computation versus Billing's per Revenue discount computation. Last resort is to do this formula: (Actual/Total Actual) *Total Discount to tally the discount with Billing. Needed to adjust field Medic_Compensable, Medic_DumpCompensable, and storeproc Medic_SavePhicSOA_Package | MJSH | Mary Joy Sayson | Done, adjustment not installed yet
2021-09-27 | - send-out materials/instructions for using Build File Caserates to Ma'am Evelyn | PMSH | Evelyn Mannzano | Done
2021-09-27 | - adjustment on stored proc Medic_CheckNearlyElapsedClaims (reading data start year to replace from 2008 to 2015, and removed isnulls in where clauses) to lessen elapsed time. To update on VSS dbase as well | LMC | Farra Palacay / Remal Oligario | Done
2021-09-24 | - trace Patient's PhilHealth deductions deficiency. Findings are, compensable some items not properly tagged in Inventory Module. Solution is to, correct the tagging and then B6recompute Patient's PhilHealth deduction. | LMC | Remal Oligario | Done
2021-09-24 | - adjustment on stored proc MedicRep_DetailedMedicareItems group empty, NULL and N values to Non-Medicare group. To update on VSS dbase as well | LMC | Remal Oligario | Done
2021-09-24 | - discuss issues/inquiries regarding with the previously installed updates. | LMC | Nida Abellera | Done
2021-09-24 | - discuss issue regarding confinement history. No problem with the system but still need sample patient for tracing since they insists. | PMSH | Nida Abellera | Done; waiting for sample patient
2021-09-24 | - to trace and delete allocated PhilHealth Payments in OR 205361, a request from the Client. Reason is to allocate the deleted payments to a new OR. Delete Billing..tbbilldailybill where Refnum = '205361' and revenueid in ('MP', 'MJ'); Delete Billing..tbbillOPDailyOut where Refnum = '205361' and revenueid in ('MP', 'MJ'); Delete Billing..tbParsLedger where Docnum = '205361' and revenueid in ('MP', 'MJ'); Delete Medicare..tbmedpayment where ORNumber = '205361'; Update Medicare..tbmeddoctors Set Ornumber = Null, Payment = Null, DatePaid = Null, WTax = Null, VAT = Null, TaxablePF = Null, Net = Null, TaxRate = Null Where Ornumber = '205361' | CHMCI | Evelyn Manzano/Krystelle Loyola(IT) | Done
2021-09-23 | - discuss implementation details for AUFMC's PNF and PMSH Upgrade and stating previous concerns about missing reports that were not written or documented. | PMSH/AUFMC | Nida Abellera | Done
2021-09-23 | - dicuss/trace allocated PhilHealth Payment for OR# 205361, entries were already in PARS Ledger so suggested to discuss it with the client and Sir JonRoss before proceeding to Client's request which is to delete allocated payment under the stated OR number. | CHMCI | Evelyn Manzano | Done
2021-09-23 | - New switch for Manual Posting of PHIC AR: INSERT [dbo].[tbMedMenu] ([MenuID], [Menu], [MenuGroup], [MainMenu], [Status]) VALUES (N'261', N'Manual Posting of PHIC Receivables', N'A', N'2', 1) | ARCH |  | Done
2021-09-23 | - automate Essential Newborn Care checklist to set value 1 when Essential Newborn Care Package is ticked regardless if patient's CF2 is already posted or not yet. Checklist: Immediate dryin of newborn, Early skin to skin contact, Timely cord clamping, Eye prophylaxis, Weighing of the newborn, Vitamin K administration, BGC vaccination, Hepatitis B Vaccination, Non-separation of mother/baby for early breastfeeding initiation. Compile new Exe File | MJSH | Mary Joy Sayson | Done
2021-09-23 | - replied inquiries regarding PNF Upgrade and other reports for revision: Medicare Items and Print Charges | AUFMC | Nhikz(phic user), Jeremiah(IT), Nida Abellera | Done
2021-09-22 | - discuss report's condition for PhilHealth Claims Monitoring Hospital, and Professional Fees | LMC | Remal Oligario | Done
2021-09-22 | - discuss RCF for Daily Transmittal Report's format and condition | BIHMI | Thea Llanado
2021-09-22 | - discuss RCF for Reports to be revise for the PNF, Non-PNF classification | AUFMC | Nida Abellera | Done
2021-09-22 | - continue working on the Manual Posting of AR for PhilHealth, new table tbMedActual_ar, tbMedDoctors_ar , storedproc Medic_SavePHICDoctor_AR | ARCH |  | Done
2021-09-22 | - adjustment and fixes on the latest update for Receivable Reports. StoredProc MedicRep_TotalReceivable, MedicRep_TotalReceivable_All, RptFile, and new exe file for affected report's options. ***Included logs in the Build File of Caserates | LMC | Nida Abellera | Done
2021-09-22 | - incorrect medicaretype tagging of DN - Doctors Discount and Pharmacy item causes the discrepancy in PhilHealth Computation. Fixed by correcting the item's tagging, then recompute PhilHealth Computation. | MCDGH | Edrian Estoque | Done
2021-09-21 | - discuss PMSH upgrade for the in coming meeting on Thursday | PMSH | Nida Abellera | Done
2021-09-21 | - discuss PMSH upgrade | PMSH | Rodney Frigillana | Done
2021-09-21 | - assist Ma;am Nida on PNF Testing, Recall requirements, and requests. | AUFMC | Nida Abellera | Done
2021-09-21 | - trace and discussion on the allocated PF Payment of patient 1743818B and if it's possible to remove the payment allocated. But was already uploaded in Accounting Module where voucher and check already made. So I suggested a signed Incident Report and request/explanation to Accounting Department must accomplish. | LMC | Nida Abellera/Roda Mejia(phic user) | Done
2021-09-21 | - discussion with Nhickz in regards with the Active discounts to be covered on Claim Form 2 , Amount After Discount | AUFMC |  | Done
2021-09-21 | - check in today's updates made for MJSH version on VSS | MJSH |  | Done
2021-09-21 | - rounded off PF PhilHealth amount to whole number concern. Adjustment on PhilHealth PF field on Doctors Tab. Revise stored proc Medic_DoctorInfo and compile new exe. added Format(Amount, "#######0.00") in loading PF amounts. Commented unnecessary stored proc to minimize loading time of Data Entry Medic_CreateTempTable, Medic_AutoComputeCharges, Medic_AutoComputeChargesOP | MJSH | Mary Joy Sayson | Done
2021-09-20 | - 'out of stack' concern in the loading of Patient's Charges with existing PHIC Deductions to Computation Table. Given instructions for troubleshooting but didn't work so, Since it's urgent, decided to manual Reset the PHIC deductions of the patient. | SLUH | Evelyn Manzano/ Edrick IT | Done
2021-09-20 | - trace and discuss regarding discrepanciesagain due to incorrect transactions in the charging/revoking/returning Supplies and Medicines. A major concern that needs to be fix | AUFMC | Nida Abellera | Done
2021-09-20 | - start to design and code Manual AR Posting of PHIC, design Table structures, Stored Proc | ARCH |  | working on
2021-09-20 | - discussion on Manual AR Posting of PHIC with Ma'am Jo and to make sample patient for Manual AR in PARS Module | ARCH
2021-09-20 | - revise condition for deleting transmittal details of patient when already sumbitted in the E-claims Module. Medic_DeleteTransmital, Medic_DeleteTransmittalLogs | LANAO | Mary Joy Sayson | Done
2021-09-17 | - discuss and assist Ma'am Farra for the table.fields reference of Chief Complaint under CF4 due to recurring concerns on "Physical Exam" as Chief Complaint that is not applicable. | LMC | Farra Mae Sanchez | Done
2021-09-17 | - extract all caserates with exempted to 24 hours restriction from live database: a request from Ma'am Ruschelle | LMC | Farra Mae Sanchez | Done
2021-09-17 | - discuss Refiling Claims (Transmittal) process after 2 re-file events are done. | BIHMI | Thea Andrea (IT) | Done
2021-09-17 | - discuss on PMSH upgrade along with what Sir Philip's commitment to them regarding PHIC. To fully use the upgraded version and maintain a unit where old PHIC Version is working. | PMSH | Nida Abellera | Done
2021-09-17 | - discuss and assist Ma'am Nida on AUF update scripts for PNF updates and other PHIC concerns | AUFMC | Nida Abellera | Done
2021-09-17 | - discuss updates for AR and Payment Reports with Ma'am Roda and Ma'am Nida | LMC | Nida Abellera | Done
2021-09-16 | - fixed positioning of fields/entries on Auto-Computation Form. Sent new exe file to Ma'am Nida | PMSH | Nida Abellera | Done
2021-09-16 | - fix and trace discrepancies on loading Actual Charges on CF2, XML, caused by TB and BB Transactions, with multiple account type. Fixed on funtion cf2_fees | AUFMC | Nida Abellera | Done
2021-09-16 | - extract data for Professional Fees Payment W/ Deduction Report, Professional Fees W/out Deduction Report with cut-off September 16-29, 2021 for Accounting purposes, requested by Ma'am Roda. sent thru email. | LMC | Roda Mejia (phic user) | Done
2021-09-15 | - discussion with Ma'am Nhickz about PHIC Circular 2020-0011 Full Financial Risk Protection For Filipino Health Workers And Patients Against Coronavirus Disease (COVID-19). and (Circular No. 2020-0009) Benefit Packages For Inpatient Care Of Probable And Confirmed COVID-19 Developing Severe Illness/Outcomes. Process on how to implement this circular in which all HMO/Insurance/Employee discounts shall be deducted first from the hospital bill before PHIC benefits. | AUFMC | Nhickz(PHIC user) | required to send RCF and initially discussed with team.
2021-09-15 | - released instructions for data checking regarding Payment Reports concerns. | ARCH | Rod Eda | Done
2021-09-15 | - inquiries regarding Payment reports condition | LMC | Roda Mejia (phic user) | Done
2021-09-15 | - compiled scripts and materials for PNF Circular testing sent to Ma'am Nida. requested Live backup to restore in Test Server. | AUFMC | Nida Abellera | Done
2021-09-15 | - inquiries regarding restoration of database backups | AUFMC | Jeremiah Gatus (IT) | Done
2021-09-14 | - creating scripts for PNF testing , advise IT to restore Live Backup to Test Server | AUFMC
2021-09-14 | - Adjustments, finalize and compile updates for LMC 1. Doctors Receivable - TBDots Patients 2. Doctors Receivable Per Doctor - TBDots TBDots Patients 3. Total Receivable by Membership Category - TBDots Patients 4. Total Receivable by Membership Category - include Actual Professional Fees - include Receivable Professional Fees 5. Total Receivable All - TBDots Patients 6. Total Receivable All - include Actual Professional Fees - include Receivable Professional Fees 7. Professional Fees Receivable Aging by Month 8. Professional Fees Receivable Aging by Year 9. Professional Fees Payments for Uploading w/ Deduction (Auto-upload in Accounting) 10. Professional Fees Payments for Uploading w/out Deduction (Auto-upload in Accounting) 11. PhilHealth Claims Monitoring Report for Hospital Bill 12. PhilHealth Claims Monitoring Report for Professional Fees | LMC | Nida Abellera | Done
2021-09-14 | - trace and fix about other HCI Discounts for Claim Form 2, Adjustment on VAT column of SOA | AUFMC | Nhickz(phic user), Jeremiah Gatus (IT) | Done
2021-09-13 | - reviewed requested Receivable and Payment reports for LMC. Finalization of updates for tomorrow's update | LMC |  | Done
2021-09-13 | - instructions given to Ma'am Nida for PPMC's request: PNF Cicrular: Medicines must be tag accordingly | PPMC | Nida Abellera | DOne
2021-09-13 | - discussion regarding PhilHealth Computation per Reveneuid to reflect on Discount Computation Table of Billing. which data are already available on PhilHealth table, just need to load and group by revenueid. | N/A | Rod Eda | Done
2021-09-13 | - recall instructions to Sir Jeremiah regarding PNF requirements. To be endorse to Pharmacy Department | AUFMC | Jeremiah Gatus (IT) | Done
2021-09-13 | - adjustment on values to be reflected on Amt After Discount (Claim Form 2) and on parameter pDiscount (XML). Function: fn_CF2Fees, and rpt file Part3and4ACR.rpt. Discussed with King, Nhickz, Jeremiah | AUFMC | Nhickz (phic user) / King Pinto | Done
2021-09-10 | - Issue: excess PHIC coverage. Traced Patient's total actual charges discrepancy due to incorrect adjustments/cancellations of pharmacy items. 6 items with incorrect adjustments. | AUFMC | Medys Team/Nida | fixed is pending
2021-09-10 | - discussion about CF2 and XML filing with Ma'am Nhickz, advised to review SOA, CF2 and XML | AUFMC | Nhickz (phic user) | Done
2021-09-10 | - discussion about PHIC Member Number duplicates. | BIHMI | Mary Joy Sayson | Done
2021-09-10 | - dicussion with Jeremiah about Inventory Module updates, entries that needs to be and how shld these be filled-out, and why does these entries matters on PNF Cicular ; did Support Coordinator's job to be exact.. | AUFMC | Jeremiah Gatus | Done
2021-09-10 | - review discussions stated on the Meeting Minutes regarding requests and issues noted by Edrian Estoque | MCDGH | Edrian Estoque | Done
2021-09-09 | - gave set of instructions on how to trace and fix problem on DIscharge Diagnosis data on CF4 |  | Nida Abellera | Done
2021-09-09 | - review updates on Total Medicare Receivable requests by Ma'am Roda | LMC |  | Pending
2021-09-09 | - trace and fix new cases concerning to SOA-CF2-XML data. Revision on conditions made from previous Updates. | AUFMC | Nhickz (Phic User), Jeremiah Gatus(IT) | Done
2021-09-09 | - to configure setting for the log in message. taking too much time to close.CurrentUser.dll new update | SGH | Nida Abellera | Done
2021-09-09 | - discussion/ recall CF4 installation implemented by Support Krys months ago. issues about RTH been raised lately due to discrepancies. | SGH | Joan Buncio, Krys, Cavin Abellana | Done
2021-09-09 | - trace/fix/discuss. Issue: RTH claims due to height and weight discrepancy; And problem on using the Philhealth program. Found out that they're not using the upgraded version that was installed months ago. To summarize: Demonstrate on how to install DLL needed, sent instructions for clean installation as what they requested. | SGH | Cavin Abellana(IT)/ Joan Buncio | Done
2021-09-08 | - dicussion on duplicate PHIC Member Number; to review Medic_SavePostedDataNew,Medic_SaveMemberinfo, for simulation to be done by support |  | Mary Joy Sayson | Done
2021-09-08 | - discussion about PNF and ARSP tagging of items, pending and status; advised Ma'am Nida to atleast give status and instructions to client and what are the possible to do's for the time being | LMC/AUFMC | Nida Abellera | Done
2021-09-08 | - follow-up ZBenefit Tagging new field |  |  | Done
2021-09-08 | - Inquiries on GPCode new format entries and CF4 display |  | Mary Joy Sayson | Done
2021-09-08 | - re-train PHIC user about CF2 filing process/ posting | AUFMC | Nhickz (Phic user) | done
2021-09-08 | - trace and fix XML and CF2 back part's discrepancy on amounts. (Found out that they're not using CF2 BACK PART ever since; not even reviewing XML data) ; Update/s on function fn_CF2Fees, stored proc Medicrep_PartIII.. Instructed to review SOA-CF2-XML files | AUFMC | Nhickz (Phic User), Jeremiah Gatus(IT) | Updates installed; Under monitoring
2021-09-08 | - discussion with Sir King for XML philhealth computation references on function fn_cf2Fees; informed for the Updates that will be impllemented today | AUFMC | King Pinto | Done
2021-09-08 | - discussion with Ma'am Nhickz about ARSP concerning on PHIC deduction and how will it affect the previous patients. | AUFMC | Nhickz (Phic user) | Done
2021-09-08 | - discussion on status/pendings for PNF Cicular Request with Ms Goria Pacheco, Jeremiah Gatus | AUFMC | Nida Abellera | Done
2021-06-29 | - traced and discussed trace results on SOA and CF2's Amount after Discount. Billing user error. Discount onf two Billing tables didn't match | WCI | Nida Abellera | Done
2021-06-29 | - adjusment on stored proc MedicRep_TotalReceivable, MedicRep_TotalReceivable_ALL | LMC |  | Done
2021-06-24 | - fixed concerns regarding garbage data; payment dated year 2003; and no traced of ORnumber in database. | LMC | Remal Oligario, Roda Mejia | Done
2021-06-24 | - traced concern on discharge date concern on SOA; to fix this any changes of discharge date or time on Medical Record should manually update it to Philhealth also | LMC | Farra Mae Palacay | Done
2021-06-24 | - inquiries and discussion on Refiled and RTH processes and reports | SLUH | Evelyn Manzano, King Pinto | Done
2021-06-24 | - traced and discussion about treatment on discounts for PHIC Computation. Issues on displaying negative amounts on Auto_computation which triggers error. the cause is that the Discount was tag as compensable. P.S. discounts except Senior and PWD is not compensable. | R1MC | Evelyn Manzano | Done
2021-06-24 | - assists on installing Philhealth module regarding DLLs. | Tagudin | Farra Mae Palacay | Done
2021-06-23 | - inquiries SOA discharge date concern | LMC | Farra Mae Palacay | to be traced tom
2021-06-23 | - inquiries and discussion on Final Diagnosis and other concerns | CDUH | Nida Abellera | pending: compiled list of concerns from client
2021-06-23 | - follow-up inquiries and discussion on Aging PF Accounts Recievable (Monthly and Yearly) Report; Formatting and analyzation of report | LMC | Roda Mejia | to be continued
2021-06-23 | - follow-up review, finalizing and creating scripts for CHMC (for testing) | CHMC |  | to be continued; testing unit not available
2021-06-22 | - inquiries and discussion on discharge date/time source on CF4 | BIHMI | Thea Llanado | Done
2021-06-22 | - fixed reported issues on testing updates | PMSH | Nida Abellera | done
2021-06-22 | - inquiries and discussion on RCF, Doctor Receivables, payment reports | LMC | Roda Mejia | done, development to be scheduled
2021-06-22 | - inquiries and discussion on CF4 Entry | AUF | Nhickz | done
2021-06-21 | - review, finalizing and creating scripts for CHMC (for testing) | CHMC |  | to be continued
2021-06-21 | - inquiries and discussion regarding on Konsulta and other pending RCF | CHDG | Hector Catbagan | to follow
2021-06-21 | - inquiries and discussion on 24 hours stay condition per ICD/RVS Code | LMC | Farra Mae Palacay | Done
2021-06-15 | - checked-in adjustment on VSS |  |  | Done
2021-06-15 | -fixes today applied to apps.gomedsys.com |  |  | Done
2021-06-15 | - traced issues on saving of manual edited of amounts on computation grid for cases higher benefits than the Net amount; to do's: adjustment on sourcecode, asking for list of concerns so will just manual update to lessen the burden of user on recomputation. | LMC | Farra Mae Palacay
2021-06-15 | - inquiries and discussion on affected tables in Recomputation process; request for revision on stored proc Medic_ReSlashing to exclude tbmedpatient and tbmeddoctors for reset. | BIHMI | Mary Joy Sayson | Done
2021-06-15 | - fixes on loading loading prev confinement. revised stored proc Medic_Confinementwithin90Days | MDH | Nida Abellera | Done
2021-06-15 | - supply outdated and missing stored procs on Member and Dependent's benefits | MDH | Nida Abellera | Done
2021-06-15 | - inquiries and discussion on 'This patient has previous confinement within 90 days'; traced questionnable account regarding on this | MDH | Nida Abellera | Done
2021-06-15 | - revised and removed lines Medic_CreateTempTable, Medic_AutoComputeCharges, Medic_AutoComputeChargesOP on Source Code; for they're the cause of slow loading of forms. | VSS |  | for next updates
2021-06-14 | -assisted Jeremiah G.(AUFMC staff) regards with issues on uploading attachments on Eclaims | AUFMC |  | Done
2021-06-14 | - assisted Nida A. to fix errors on installing updates on Test Server | PMSH | Nida Abellera | Done
2021-06-14 | - revised stored proc Medic_InsertUpdateForm1. To included table tbmedpatient.membertype on updating changes on Form 1 Entry (PS, if and only if patient is not yet transmitted); To include logs also. | BIHMI | Mary Joy Sayson | Done, Sent updates.
2021-06-14 | - traced issue with Old Patient's records/charges year 2012; SOA and Philhealth doesn't match | BIHMI | Mary Joy Sayson | no feedback from IT
2021-06-14 | - revised stored proc Medic_Reslashing for recomputation of Patient's old record. | BIHMI | Mary Joy Sayson | Done
2021-06-14 | - inquiries and discussion with Krys R. and Stephanie B. the old NBB process of the Clients. | MEDSYS
2021-06-14 | - traced patient's pf charges in connection with Payment Register Report; Result to that, Patient's PF charges are confusing, firstly the user charged a negative amount that shld be a positive, then cancelled it, then charged again with higher and negative amount (that shld be positive also), lastly charged again with higher and positive amount. that if you sum up those, you will get a negative amount. This matter in PHIC computation, because if the actual amount is equal or lesser than 0, it will not allow to insert data(Philhhealth Benefit) on Billing table. For the solution,the user shld correct the PF charges and Philhealth re-computation must be done. | Tagudin | Remal Oligario | No feedback
2021-06-14 | - revised retreiving of patient charges on Data Entry(CF2) due to slow loading of data; removed stored proc Medic_AutoComputeCharges and Medic_AutoComputeChargesOP upon form loading | LMC/Tagudin/VSS Clients | none | for next update
2021-06-11 | - Revised and finalized updates for the RCF pertaining to: Allow Editing of Philhealth Amount on Auto-Computation grid; this is for Packages with conditions on availment of full package amount like Newborn packages | MDH | Nida Abellera | Done; Update sent and for testing
2021-06-11 | - revised NewClaimForm2ACR.rpt for fixes on Laterality check boxes | ARCH | Rodrigo Eda | Done
2021-06-09 | - revised NewClaimForm2ACR.rpt and function fn_isCOVIDCode for new basis of using Accreditation code for Covid cases | ARCH | Rodrigo Eda | Done, tested and installed updates by yours truly
2021-06-09 | - discussion and inquiries on generating of MMHR; sent a copy of latest MandatoryReportBackNew.rpt | BIHMI | Mary Joy Sayson | Done
2021-06-07 | - revised NewClaimForm2ACR.rpt and stored proc Medic_LoadPHIC_CF4 , and created new function fn_isCOVIDCode. Use 'C19%' as basis. This revision is for the request on the usage of C07031361 as HCI Accreditation code for COVID cases. | ARCH | Rodrigo Eda | Done, sent updates
2021-06-07 | - discussed to Rodrigo E. the inquiry for the distribution of HCI and PF Benefits of the new Covid case C19CIS | ARCH | Rodrigo Eda
2021-06-04 | - discussed the things needs to revise and basis for the request of using C07031361 as HCI Accreditation; gathering of data | ARCH | Rodrigo Eda | Done
2021-06-02 | - assisted Rod E for extracting PhilHealth Caserates, procedures and medical cases from database |  | Rodrigo Eda | Done
2021-06-01 | - inquiries and discussion on MMHR, Updating of CF1 effect in CF2 posting | BIHMI | Mary Joy Sayson | Done
2021-05-31 | - inquiries, tracing and dicussion on saving of PF decimal values, revised setup from roundind off to whole number to nearest hundredths; adjustments on SourceCode. | MJSH | Mary Joy Sayson | Done, Updates sent
2021-05-28 | - sick leave
2021-05-25 | - tracing and adjustment on Source Code for claim cases with using same ICD/RVS code on both First and Second Package codes ; sent exe file | BIHMI | Thea Llanado/ Mary Joy Sayson | Done
2021-05-25 | - discussion for the request of Eclaims, CF2, CSF, CF4's accreditation updates | ARCH | Rodrigo Eda | Done
2021-05-24 | - inquiries and discussion for COVID accreditation updates request | ARCH | Rodrigo Eda | Done
2021-05-20 | - inquiries and discussion for ICD10 Code in Medical Records and Philhealth, and the Consent to APR entry |  | Rodrigo Eda
2021-05-19 | - revised to set default date as current date on Form1 Entry Received field | ARCH | Rodrigo Eda | Done, for next update
2021-05-18 | - fixed bugs on retrieving inventory items with no LocationID; revised stored proc Medic_SavePHIC_Package | BIHMI | Mary Joy Sayson | Done, installed by yours truly
2021-05-18 | - inquiries and discussion on application of NET of Discount policy per Client, fixed 'invalid procedure call' error upon applying Philhealth Benefits; This occurs when Actual Charges have negative value due to NET of Discount policy; revised stored proc Medic_InsertTempTable | CDUH | Krysmeen Rabo/ Mary Joy Sayson | Done
2021-05-17 | - inquiries and discussion on which database backup to use for MCT installations. |  | Mary Joy Sayson
2021-05-14 | - traced and fixed Patient's Account with issues on Philhealth Benefits application; revised Medic_SavePHICSOA_Package; Philhealth recomputation needs to be done | BIHMI | Thea Llanado/ Mary Joy Sayson | Done
2021-05-12 | - retreiving null records, get latest copy of Medic_GetDoctorPF on Apps | ARCH | Rodrigo Eda | Done
2021-05-12 | - fixed blank discharge date and time on CF4, revised stored proc Medic_LoadPHIC_CF4 | ARCH | Rodrigo Eda | Done
2021-05-12 | - inquiries and discussion for prjgridentry.ocx usage of Philhealth and Inventory Module | ARCH | Rodrigo Eda
2021-05-10 | - inquiries and discussion for Patient Account's Philhealth adjustment with closed account | ARCH | Rodrigo Eda | Done
2021-05-06 | - inquiries and discussion for PCR Patient with cancellation of Philhealth Benefits after Claims is already submitted; manual delete record requested by client | ARCH | Rodrigo Eda | Done
2021-05-05 | - traced Patient's charges disrepancy on PhilHealth computations; discussed to Mary Joy what needs to be done to fix it.. This case occurred due to Laboratory item that was charged once but cancelled twice so it became negative. | BIHMI | Mary Joy Sayson | Done
2021-05-05 | - revised CF4 page 2, added Recovered field for OutCome | MDH, PPMC | Nida Abellera | Done; will apply to all client
2021-05-05 | - released script to trace logs for Dischargedate concerns on PHIC Data Entry and SOA; inquiries and discussion on how to address this matter | ARCH | Rodrigo Eda | Done
2021-05-05 | - follow-up PHIC SOA concern to Remal; and commented additional instructions | LMC | Remal Oligario | Done; no feedback yet from user side
2021-05-04 | - discussed on how data shld be encoded in Data Entry- Diagnosis , an ICD with multiple Procedures |  | Mary Joy Sayson
2021-05-03 | - traced Patient's charges with tally discrepancies on PhilHealth Covered amounts; just needed to recompute due to changes on Patient;s charges. | MGDGH | Krysmheen Raboy | Done
2021-05-03 | - traced Patient's charges with tally discrepancies on Amt After Discount; - released set of intructions and script for fixing/ checking/tracing this kind of concern. | MCDGH | Krysmheen Raboy | Done
2021-04-30 | - released exe file for bug fix on loading data on grid (Batch Payment Entry - Search Philhealth Member/Patient) | ARCH | Rodrigo Eda | Done
2021-04-28 | - inquiries and discussion on HCI discounts, revised fn_CF2Fees | CHMCI | Rodrigo Eda | Done
2021-04-27 | - revised MedicRep_PartIII to use Fn_CF2Fees for HCI Actual Amount; in conclusion for the discrepancy of SOA and CF2 was, revenueid WT needs to be fix where shld be displayed on SOA. | MJSH | Mary Joy Sayson | Done; support forwarded this issue to Finance Programmer
2021-04-27 | - revised Function fn_CF2Fees for HCIActualAmount to exclude MP/MJ revenueids | CHMCI | Rodrigo Eda | Done
2021-04-13 | - released rpt file for "Script Out Of Range" error on CF2; together with exe file to keep them updated | CHDG | Hector Catbagan | Done
2021-04-13 | - discussed PHIC Member Number issues with King and Nida | PPMC | King Pinto, Nida Abellera | Done
2021-04-13 | - reviewed cf4 scripts for Brokenshire concerning to it's Execution Time that took too long | BIHMI | Mary Joy Sayson | Done
2021-04-13 | - included 2 fields to empty value every "Recompute" button is used: cmbpackage(0), cmbpackage(1) | LMC | Remal Oligario | Done; will apply to all version
| - released exe file for the new update |  |  | Done
2021-04-12 | - released a script to check the philhealth computation amount concerning PARS SOA and PHIC SOA | CHMC | Evelyn Manzano | No feedback, no access with Client's Remote Unit
2021-04-12 | - revised sourcecode and storedproc Medic_SavePostedDataNew to fix bug on editing of Discharge date and time in DataEntry (SOA and CF2 must be based on what are encoded here, not on Admission or Medical Record Module); released exe file and storeproc | PPMC | Nida Abellera | Done
2021-04-12 | - released rpt file for "Script Out Of Range" error on CF2 | PPMC | Nida Abellera | Done
2021-04-12 | - inquiries and discussions of preparation, SOP's for the CF4 Updates before going Live. especially concerning on units with multiple modules installed | NKTI | Mariz Luis | Done
2021-04-12 | - released CF4 Updates: Exe, Reports and Scripts | NKTI | Mariz Luis | Done
2021-04-12 | - revised StoredProc for Computation concerning to discrepancies in SOA | CHDG | Hector Catbagan | Done
| - revised rpt file for Split SOA for negative amounts after PHIC Deduction; some cases with Higher Package Amount than the Actual Charges. |  |  | Done
2021-04-12 | - revised storedproc for NBB cases with Doctors with PF Benefits shld show on Claim Signature Form: Medic_InsertDocDumpTable, Medic_GetDoctorPF | LANAO | Mary Joy Sayson | Done

## Off-set
Offset Date | Offset Date(used)
2021-10-02
2021-11-30